## List_1 Risk Register
Risk Id | Risk Decription | Likeli hood | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
1 | Project purpose and need is not well-defined | Medium | High | High | Schedule, Cost, Quality | Project sponsor | Complete a business case if not already provided and ensure purpose is well defined on Project Charter | Escalate to the Project Board with an assessment of the risk of runaway costs/never-ending project. | Business case re-written with clear deliverables and submitted to the Project Board for approval. | open
2 | Project design and deliverable definition is incomplete | Low | High | High | Schedule, Cost, Quality | Project sponsor | Define the scope in detail via design workshops with input from subject matter experts | Document assumptions made and associated risks. Request high risk items that are ill-defined are removed from scope. | Design workshops scheduled. | open
3 | Tight time limits that influence the testing flow | Medium | High | High | Cost, Schedule, Quality | Project sponsor | ■ Following the development schedule. ■ Timely notification of potential problems or shifts in the schedule. | Consider insurance and use Project Board to get advance notice if possible. | Project Board reviewing insurance options. | open
Risk Id | Risk Decription | Likelihood | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
4 | Incorrect or imcomplete stated requirements | High | High | High | Cost, Schedule | Project manager | ■ Ensure that all the requirements are fully laid out in one spot, and all the necessary information is present. ■ Generate discussion on potential failure points and exposures to ensure they will either be addressed via controls and/or risk strategies. ■ Conducting a requirement risk assessment | ■ Establish processes and procedures to handle occuring requirements' risks, ■ Include contingency time in schedules to handle likely delays due to additional time need for reconsidering project's requirements. ■ Additional unscheduled meeting arrangement for the final project's requirements's approval. |  | open
Risk Id | Risk Decription | Likelihood | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
5 | Changes in the requirements during developing | High | High | High | Cost, Schedule | Project manager | ■ Fixing the basic list of requirements in the contract. ■ Frequent demonstrations of new functionalities. | ■ Establish processes and procedures to handle occuring requirements' risks, ■ Include contingency time in schedules to handle likely delays due to additional time need for reconsidering project's requirements. ■ Additional unscheduled meeting arrangement for the final project's requirements's approval. |  | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
6 | Late submission of the information, delays in document approval by the Customer | Medium | High | High | Schedule | Project manager | ■ Complience with the rules of meetings management. ■ Meetings' scheduling and the provision of the necessary information in advance. ■ Timely information about the employees' unavailability. | Escalate to Project Sponsor and Contracts Manager. Implement late clauses. | Lead time from each contractor built into the project schedule. Late penalties agreed to and contracts signed. | open
7 | Problems with the delivery of the product into production because of the unavailability of servers | High | Medium | High | Schedule | Project manager | Getting further details on installing the product from the Custiomer's IT department as soon as possible | Have a well-documented procedure and people trained to put the standby server into production, and initiating replication, enabling the jobs with minimal downtime. |  | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
8 | Pressure to arbitrarily reduce task durations and or run tasks in parallel which would increase risk of errors | Low | High | High | Schedule, Cost, Quality | Project manager | Share the schedule with key stakeholders to reduce the risk of this happening. Patiently explain that schedule was built using the expertise of subject matter experts. Explain the risks of the changes. | Escalate to Project Board with assessment of risk and impact of the change. Hold emergency risk management call with decision makers & source of pressure and lay out risk and impact. | Awaiting completion of the schedule. | open
9 | Business Case becomes obsolete or is undermined by external or internal changes | Low | High | High | Schedule, Cost, Quality | Project sponsor | No ability to reduce likelihood, but make sure early warning is given by reviewing business case on regular basis with the Project Board. | Initiate escalation and project close down procedure | Project close down procedure confirmed with Project Board. | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
10 | Scope Creep | Medium | High | High | Schedule, Cost | Project manager | Document the project scope in a Project Initiation Document or Project Charter and get it authorised by the Project Board. Refer to it throughout the project and assess all changes against it also ensuring alignment of any changes with the Business Case. | Document each and every example of scope creep NO MATTER HOW SMALL in a change request and get authorisation from the Project Board BEFORE STARTING WORK. This includes ZERO COST changes. | Scope clearly defined in the PID. | open
11 | Delay in earlier project phases jeopardizes ability to meet fixed date. For example, delivery of just in time materials, for conference or launch date. | Medium | High | High | Schedule, Cost | Project manager | Ensure the project plan is as accurate as possible using scheduling workshops and work breakdown structure. Use Tracking Gantt and Baseline to identify schedule slippage early. | Consider insurance to cover costs and alternative supplier as a back up. | Awaiting completion of the schedule. | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
12 | Theft of materials, intellectual property or equipment. | Low | High | High | Schedule, Cost, Quality | Project manager | Follow security procedures, ensure Non-Disclosure Agreements, & compliance certificates are in place. Verify all physical security measures in place. Secure insurance. | Notify appropriate authorities e.g. police, Project Board and initiate internal investigations. | NDAs issued. Security certificates confirmed for contractors | open
13 | Force majeure circumstances, like extreme weather, earthquakes that lead to loss of resources, materials, premises etc. | Low | High | High | Schedule, Cost, Quality | Project manager | Check insurance is in place. Familiarise project team with emergency procedures. When cost effective put back up systems in place e.g. generators. | Notify appropriate authorities. Follow health and safety procedures. Notify stakeholders and Project Board. | Public Liability Insurance confirmed along with additional premises insurance at site B. | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
14 | Stakeholder action delays project. | Low | High | High | Schedule, Cost, Quality | Project manager | Identify stakeholders, analyse power and influence and create a Stakeholder Engagement Plan. Project Board to authorise the plan. Revisit the plan at regular intervals to check all stakeholders are managed. Consider getting insurance. | Notify appropriate authorities and follow internal procedures e.g. for activist demonstrations. | Stakeholder Analysis in progress. | open
15 | Project schedule is not clearly defined or understood | Low | Medium | Medium | Schedule, Cost, Quality | Project manager | Hold scheduling workshops with the project team so they understand the plan and likelihood of missed tasks is reduced | Revisit the schedule with the project team. 'Relaunch' the project schedule. | Workshops scheduled. | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
16 | Lack of communication, cause lack of clarity and confusion | Medium | Medium | Medium | Schedule, Cost, Quality | Project manager | Write a communication plan which includes: the frequency, goal, and audience of each communication. Identify stakeholders early and make sure they are considered in the communication plan. Use most appropriate channel of communication for audience e.g. don't send 3 paragraph email to Developers, have a call instead. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly using assistance from Project Sponsor if needed. | Communication plan in progress. | open
Risk Id | Risk Decription | Likelihood of the Risk occuring | Impact | Severity | Effect on Cost/ Schedule/ Quality | Risk manager | Mitigation actions | Contingent action | Progress on actions | Status
17 | Added workload or time requirements because of new direction, policy or statute | Low | Medium | Medium | Schedule, Cost, Quality | Project manager | No ability to reduce likelihood. | Consider insurance and use Project Board to get advance notice if possible. | Project Board reviewing insurance options. | open
18 | Unresolved project conflicts not escalated in a timely manner | Low | Medium | Medium | Schedule, Cost, Quality | Project manager | Hold regular project team meetings and look out for conflicts. Review the project plan and stakeholder engagement plan for potential areas of conflict. | When aware immediately escalate to Project Board and gain assistance from Project Sponsor to resolve the conflict. | Project team meetings scheduled. | open
19 | Legal action delays or pauses project | Low | Medium | Medium | Schedule, Cost, Quality | Project Sponsor | Ensure all contracts signed before starting the project. Follow all regulatory requirements and complete stakeholder management plan. | Escalate to Project Board who will notify legal department. Follow instructions from legal. | Contracts issued.. | open
DICTIONARY
| Project Sponsor | The person ultimately responsible for the success of the project. The Project Sponsor is the owner of the project business case, the final decision maker and likely the holder of the ‘purse strings’.
| Business case | It states the justification for a project in terms of measurable benefits versus costs. It should include the reason for the project, the options considered, a cost vs. benefits analysis, key milestones, risks and resourcing requirements.
| Scope creep | It is the adding of features and functionality (project scope) without addressing the effects on time, costs, and resources, or without customer approval. Remember that scope creep is adding unauthorised features so the risk can be mitigated by documenting each and every example of scope creep NO MATTER HOW SMALL in a change request and getting authorisation from the Project Board BEFORE STARTING WORK. This includes ZERO COST changes.
| PID | stands for Project Initiation Document. The PID forms the basis for the management of a project.
Resources referencies:
1 | @20 Common Project Risks https://www.stakeholdermap.com/risk/register-common-project-risks.html
2 | https://www.stakeholdermap.com/project-dictionary/project-sponsor-meaning.html
3 | Source: Business Case Template ¦ Free Download - for Projects and Programmes https://www.stakeholdermap.com/project-templates/business-case-template.html
4 | Uncover gaps in your requirements using requirements risk management techniques: https://www.pmi.org/learning/library/uncover-gaps-requirements-risk-management-9910

## List_2 Requirements Charact-s
Characteristics of Testing Requirements
Feature | Description
Single responsibility | A requirement describes one thing, and one thing only.
Completeness | A requirement is fully laid out in one spot, and all the necessary information is present.
Consistency | A requirement does not contradict other requirements and fully complies with external documentation.
Atomicity | A requirement can’t be divided into several more detailed requirements without losing completeness.
Traceability | A requirement fully or partially complies with business needs as stated by the stakeholders and is documented.
Relevance | A requirement hasn’t become obsolete after time has passed.
Feasibility | A requirement can be realized within the given project.

## List_3 Test status reporting
Test status reporting
1 | Testing plans
№ | Plan's questions
1 | What are you going to do next week?
2 | What were initial plans?
3 | Should plans be adjusted based on current status?
2 | Quality
№ | Quality questions
1 | Did we find more than usual/ less bugs?
2 | Is any testing blocked?
3 | Is quality acceptable for the current stage?
4 | Do we worry about quality in some area? Why?
5 | Does any area seem worse than the rest? Why?
6 | Are developers fixing more/ less bugs than usual?
7 | Are many bugs reopened?
8 | Are we finding more bugs than are fixed?
9 | What kind of bugs are we finding? (Severity, affected functionality)
10 | Does quality change over time? How?
3 | Problems and serious risks
№ | Problems and serious risks | Description
1 | Deliveries needed | 1. What promises are still opened
2. What documents are still needed
3. What functions are still uncoded
4. What tools are not yet working
2 | Decisions needed
3 | Bugs fixes needed
4 | Serious issues with quality
5 | Unexpected problems
6 | Anything resolved from last week
Risks ahead
1 | Can anything really bad happen next week?
2 | Should something be done now to prevent it?